## Sheet1
0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39
|  |  |  | basis variant |  |  |  |  | alternative 1 |  |  |  |  | alternative 2 |  |  |  |  | alternative 3
| Project ID | Name | Followers | Base_Duration | Base_Cost | technology | quality | risk | Base_Duration | Base_Cost | technology | quality | risk | Base_Duration | Base_Cost | technology | quality | risk | Base_Duration | Base_Cost | technology | quality | risk
| 1 | Design/Entwurf | 3; 4; 5; 6; 7 | 8 | 210 | 0 | 0 |  | 6 | 320 | -1 | -1 |  | 5 | 380 | -2 | -2 |  | 10 | 190 | 1 | 1
| 2 | Projektmanagement |  | 65 | 400 | 0 | 0 |  | 40 | 430 | 1 | 1 |  | 40 | 450 | 2 | 2 |  | 40 | 500 | 2 | 1
| 3 | Entwicklung Stahlstützen | 8; 9; 10;16 | 7 | 130 | 0 | 0 |  | 6 | 150 | 0 | 0 |  | 5 | 190 | 0 | 0 |  | 9 | 110 | 1 | 1
| 4 | Entwicklung Fahrweg | 8; 9; 10; 12 | 6 | 90 | 0 | 0 |  | 5 | 140 | -1 | 0 |  | 4 | 170 | -1 | 0 |  | 7 | 100 | 1 | 1
| 5 | Entwicklung Fahrzeuge | 8; 9; 10; 13 | 7 | 120 | 0 | 0 |  | 6 | 170 | -1 | -1 |  | 4 | 210 | -1 | -2 |  | 8 | 120 | 2 | 1
| 6 | Entwicklung Elektrik & Steuerung | 8; 9; 10; 19 | 5 | 80 | 0 | 0 |  | 5 | 100 | 0 | 0 |  | 4 | 140 | 0 | 0 |  | 7 | 70 | 0 | 1
| 7 | Herrichtung der Baustelle | 11 | 3 | 90 | 0 | 0 |  | 2 | 130 | 0 | 0 |  | 1 | 190 | 0 | 0 |  | 5 | 80 | 0 | 0
| 8 | Entwicklung Katapult | 20 | 4 | 180 | 0 | 0 |  | 3 | 240 | -1 | 0 |  | 2 | 400 | -1 | 0 |  | 5 | 160 | 1 | 1
| 9 | Spezifikation Software | 14 | 6 | 40 | 0 | 0 |  | 5 | 60 | 0 | 0 |  | 4 | 70 | 0 | 0 |  | 8 | 40 | 0 | 0
| 10 | Entwicklung Soundsystem | 22 | 8 | 240 | 0 | 0 |  | 8 | 300 | 2 | 1 |  | 6 | 380 | -2 | -2 |  | 9 | 320 | 2 | 1
| 11 | Aushub Fundamente | 15 | 4 | 260 | 0 | 0 |  | 3 | 310 | 0 | 0 |  | 2 | 390 | 0 | 0 |  | 6 | 220 | 0 | 0
| 12 | Umbau Fertigung Fahrweg | 17 | 5 | 90 | 0 | 0 |  | 4 | 140 | -1 | -1 |  | 3 | 190 | -1 | -1 |  | 7 | 90 | 1 | 1
| 13 | Umbau Fertigung Fahrzeuge | 18 | 6 | 70 | 0 | 0 |  | 5 | 120 | -2 | -1 |  | 3 | 160 | -2 | -1 |  | 8 | 80 | 2 | 2
| 14 | Programmierung Software | 21 | 21 | 270 | 0 | 0 |  | 18 | 340 | 0 | 0 |  | 16 | 410 | -1 | 0 |  | 24 | 260 | 1 | 0
| 15 | Fundamente betonieren | 23 | 8 | 380 | 0 | 0 |  | 7 | 420 | 0 | -1 |  | 5 | 490 | 0 | -2 |  | 10 | 360 | 0 | 2
| 16 | Fertigung Stahlstützen | 24 | 16 | 1100 | 0 | 0 |  | 16 | 1250 | 0 | -2 |  | 12 | 1350 | 0 | -2 |  | 22 | 950 | 0 | 2
| 17 | Fertigung Fahrweg | 26 | 16 | 900 | 0 | 0 |  | 15 | 950 | 0 | 0 |  | 12 | 1000 | -2 | -2 |  | 18 | 820 | 2 | 1
| 18 | Fertigung Fahrzeug 1 als Prototyp | 27 | 17 | 280 | 0 | 0 |  | 15 | 390 | -2 | -1 |  | 13 | 430 | -3 | -3 |  | 19 | 300 | 2 | 1
| 19 | Fertigung Elektrikt und Steuerung | 28; 29 | 8 | 160 | 0 | 0 |  | 7 | 190 | 0 | -1 |  | 6 | 220 | 0 | -1 |  | 10 | 150 | 0 | 2
| 20 | Fertigung Katapult | 29 | 20 | 340 | 0 | 0 |  | 18 | 420 | -1 | -1 |  | 16 | 480 | -2 | -2 |  | 22 | 350 | 2 | 1
| 21 | Test Software | 25 | 4 | 60 | 0 | 0 |  | 3 | 90 | 0 | -1 |  | 2 | 130 | 0 | -1 |  | 6 | 70 | 0 | 2
| 22 | Fertigung Soundsystem | 31 | 15 | 180 | 0 | 0 |  | 14 | 200 | -2 | -2 |  | 12 | 270 | -3 | -3 |  | 17 | 200 | 2 | 2
| 23 | Erstellung Bauten/Station | 32 | 16 | 600 | 0 | 0 |  | 14 | 690 | 0 | -1 |  | 11 | 790 | 0 | -2 |  | 19 | 620 | 0 | 2
| 24 | Montage Stahlstützen | 26 | 8 | 290 | 0 | 0 |  | 7 | 360 | 0 | -1 |  | 5 | 490 | 0 | -2 |  | 10 | 300 | 0 | 1
| 25 | Dokumentation Software | 30 | 3 | 20 | 0 | 0 |  | 2 | 30 | 0 | 0 |  | 1 | 50 | 0 | 0 |  | 5 | 20 | 0 | 0
| 26 | Montage Fahrweg | 33; 34 | 14 | 280 | 0 | 0 |  | 12 | 380 | -1 | -1 |  | 10 | 470 | -2 | -2 |  | 16 | 290 | 2 | 2
| 27 | Montage Fahrzeug 1 - Prototyp | 33; 34 | 9 | 60 | 0 | 0 |  | 8 | 90 | 0 | -1 |  | 7 | 130 | 0 | -2 |  | 10 | 60 | 0 | 1
| 28 | Montage Elektrik und Steuerung | 33; 34 | 7 | 50 | 0 | 0 |  | 6 | 70 | 0 | 0 |  | 5 | 80 | 0 | -1 |  | 9 | 50 | 0 | 1
| 29 | Montage Katapult | 33; 34 | 8 | 40 | 0 | 0 |  | 7 | 60 | 0 | -1 |  | 5 | 110 | 0 | -2 |  | 10 | 50 | 0 | 2
| 30 | Installation Software | 33; 34 | 2 | 30 | 0 | 0 |  | 2 | 20 | 0 | -1 |  | 1 | 50 | 0 | 0 |  | 4 | 30 | 0 | 2
| 31 | Montage Soundsystem | 33; 34 | 10 | 140 | 0 | 0 |  | 9 | 190 | -2 | -1 |  | 7 | 220 | -3 | -1 |  | 12 | 150 | 2 | 1
| 32 | Installation Energieversorgung | 33; 34 | 6 | 340 | 0 | 0 |  | 5 | 370 | 0 | 0 |  | 4 | 410 | 0 | -2 |  | 8 | 360 | 0 | 2
| 33 | Funktionstest A | 35; 36 | 3 | 110 | 0 | 0 |  | 2 | 160 | -1 | -1 |  | 1 | 200 | -2 | -2 |  | 5 | 120 | 2 | 2
| 34 | Funktionstest B | 37 | 4 | 40 | 0 | 0 |  | 3 | 90 | 0 | 0 |  | 2 | 130 | -1 | -1 |  | 5 | 90 | 1 | 1
| 35 | Fertigung Fahrzeuge 2 bis 4 | 38 | 5 | 210 | 0 | 0 |  | 4 | 240 | 0 | 0 |  | 3 | 280 | 0 | 0 |  | 6 | 220 | 2 | 1
| 36 | Anpassung nach Test A | 38 | 3 | 70 | 0 | 0 |  | 2 | 80 | 0 | -1 |  | 1 | 110 | 0 | -1 |  | 4 | 70 | 1 | 2
| 37 | Anpassung nach Test B | 38 | 3 | 50 | 0 | 0 |  | 2 | 60 | -1 | 0 |  | 1 | 100 | -1 | 0 |  | 4 | 60 | 1 | 0
| 38 | Volltest / Systemtest | 39; 40; 41; 42; 43 | 3 | 90 | 0 | 0 |  | 2 | 170 | 0 | 0 |  | 1 | 240 | 0 | 0 |  | 4 | 100 | 2 | 1
| 39 | Anpassung Fahrweg | 44 | 3 | 60 | 0 | 0 |  | 2 | 90 | -1 | -1 |  | 1 | 160 | -2 | -2 |  | 5 | 90 | 2 | 2
| 40 | Anpassung Fahrzeuge | 44 | 3 | 45 | 0 | 0 |  | 2 | 60 | -2 | -1 |  | 1 | 130 | -3 | -2 |  | 4 | 60 | 2 | 1
| 41 | Anpassung Software/Steuerung | 44 | 4 | 65 | 0 | 0 |  | 3 | 70 | 0 | 0 |  | 2 | 110 | 0 | 0 |  | 5 | 60 | 1 | 1
| 42 | Systemdokumentation | 44; 45 | 3 | 50 | 0 | 0 |  | 2 | 90 | 0 | 0 |  | 1 | 120 | 0 | 0 |  | 4 | 50 | 0 | 0
| 43 | Grünflächen/Asphalt/Zaun | 46 | 3 | 70 | 0 | 0 |  | 2 | 100 | 0 | -1 |  | 1 | 140 | 0 | -2 |  | 5 | 60 | 0 | 2
| 44 | Abnahme TÜV | 46 | 2 | 35 | 0 | 0 |  | 1 | 70 | 0 | 0 | [6 empty] | 3 | 30 | 0 | 0
| 45 | Einweisung und Schulung | 46 | 2 | 40 | 0 | 0 |  | 1 | 60 | 0 | 0 | [6 empty] | 3 | 30 | 0 | 0
| 46 | Abnahme/Übergabe an Auftraggeber |  | 1 | 30 | 0 | 0 |  | 0 | 150 | 0 | 0