## First Sheet
EventID | Option | EventType | EventAccessLevel | AvailableFrom | Condition | Description | ImagePicture
1 | n |  | 0 |  | ScoreMorale<50 AND (Time>74 and Time<150) | Warning: morale is suffering under your iron hand; perhaps a more sympathetic approach would oil the wheels of progress!
2 | n |  | 1 |  | ScoreMorale<50 AND (Time>149 and Time<250) | Warning: morale is suffering under your iron hand; perhaps a more sympathetic approach would oil the wheels of progress!
3 | n |  | 0 |  | ScoreTime<52 AND (Time>74 and Time<150) | Warning: delays are starting to accumulate.
4 | n |  | 1 |  | ScoreTime<52 AND (Time>149 and Time<250) | Warning: delays are starting to accumulate.
5 | n |  | 0 |  | ScoreCost<50 AND (Time>74 and Time<150) | Warning: project funding is running out!
6 | n |  | 1 |  | ScoreCost<50 AND (Time>149 and Time<250) | Warning: project funding is running out!
7 | n |  | 0 |  | ScoreAcceptance<50 AND (Time>74 and Time<150) | Warning: the indications are that users are not too happy with the project.
8 | n |  | 1 |  | ScoreAcceptance<50 AND (Time>149 and Time<250) | Warning: the indications are that users are not too happy with the project.
9 | n |  | 0 |  | ScoreQuality<55 AND (Time>74 and Time<150) | Warning: the technical quality of the project is becoming marginal!
10 | n |  | 1 |  | ScoreQuality<55 AND (Time>149 and Time<250) | Warning: the technical quality of the project is becoming marginal!
11 | n |  | 0 |  | ScoreSecurity<50 AND (Time>74 and Time<150) | Warning: the security of the project is low!
12 | n |  | 1 |  | ScoreSecurity<50 AND (Time>149 and Time<250) | Warning: the security of the project is low!
13 | y |  | 1 |  | Time=50 | Don't forget you can use the management initiatives to create your own opportunities to control performance.
14 | n |  | 0 |  | Time=140 | Opportunity to spend two days in quality circle meetings to increase the quality of the current activities.
16 | n |  | 1 |  | TaskTime(8)=10 | It is evident that some of the programmers are drinking heavily in the lunchtimes. Quality is likely to suffer.
17 | y |  | 0 |  | TimeLag=3 | The drinking continues. The quality of programming has gone down and you hear that the offenders are laughing behind your back.
18 | y |  | 0 |  |  | Your firm action put a stop to the drinking and work can continue even if a few people got upset.
21 | n |  | 0 |  | TaskTime(17)=3 | You get an e-mail from the M.D. during task 17 ; she would like to come on a walkabout to raise the profile of the project (and the M.D.) and pose in front of some screens for the firm's newsletter.
22 | n |  | 1 |  | TaskTime(10)=22 | Integration testing is proving difficult. The lead tester approaches you and asks for an extension to daily breaks from 30 minutes to one hour. She argued that productivity might actually improve.
23 | y |  | 1 |  |  | You're a hard manager and morale has taken another tumble after your refusal to extend the breaks; quality is suffering too.
24 | y |  | 1 |  |  | A good move to support the extended breaks - the staff appreciate your support. Morale is up, quality is up and 3 days are saved in task 9 as a result.
27 | n |  | 1 |  | TaskTime(4)=3 | It is reported to you that rumours are spreading amongst the system design team about the financial viability of the project. There is talk of contracts being curtailed. This is all news to you!
28 | y |  | 1 |  | TimeLag=1 | Smart move to deal with the rumours Boss. Your staff meeting has dispelled the rumours, and progress can be made.
29 | y |  | 1 |  | TimeLag=1 | The rumours are getting worse; quality and morale are suffering during system design as a result .
30 | y |  | 1 |  | TimeLag=1 | Fortunately it appears as if the rumours are subsiding.
31 | n |  | 1 |  | TaskTime(2)=3 | It is winter and the heating systems have failed during functional specification. Working conditions are very difficult to say the least!
32 | y |  | 1 |  |  | The team turn up but within an hour are so fed up with the cold that they ask for permission to quit work for two days until the heating is mended. What will your response be, Boss?
33 | y |  | 1 |  |  | Your hard line attitude about working conditions has provoked a confrontation. The team representative threatens to lead the functional specification team off site unless you do something.
34 | y |  | 1 |  |  | The team did not walk out. You got away with it this time!
35 | y |  | 1 |  |  | The team leader was serious and the team has walked off site, shivering! You have to spend most of the week persuading them back and have lost significant credibility and rapport.
36 | n |  | 1 |  | TaskTime(15)=6 | Programmers report an undocumented routine in a utility program they were amending for the new system during data conversion testing.
37 | y |  | 0 |  |  | The test program crashes out due to data type mismatches. The undocumented routine performed some crucial data conversions to patch previous bugs.
38 | y |  | 0 |  |  | The undocumented routine performed some crucial data conversions to patch previous bugs. Good job you were careful or you would have lost even more time and money.
39 | n |  | 1 |  | TaskTime(6)=11 | The hardware supplier has delivered the wrong machine: it has only 90% of the i-o capacity you ordered.
40 | y |  | 0 |  | TaskTime(17)=1 | Remember that deep blue but under-powered machine you accepted? It crashed under a heavy load of transactions on the first day's acceptance testing.
41 | n |  | 0 |  | TaskTime(8)=20 | Your quality manager advises an early pre-test of the core modules during programming whilst rectification of any problems is relatively easy.
42 | y |  | 0 |  | TimeLag=5 | The pre-testing reports only slight defects in core module data definitions, but your quality manager has a worried look on her face.
43 | y |  | 0 |  | TaskTime(10)=5 | Integration testing shows data corruption related to the core module functionality. Your quality manager is fuming because you ignored her advice, and the team is unhappy.
44 | y |  | 0 |  | TimeLag=5 | It is time to progress your meeting about the pre-testing of the core modules, which has not yet occurred.
45 | y |  | 0 |  | TimeLag=1 | At the meeting about the pre-testing of the core modules the team suggests an initial test on a small section taking only 2 days and costing £2k.
46 | y |  | 0 |  | TimeLag=1 | The team insist that there is no need for action nor even a meeting about this matter.
47 | n |  | 0 |  | TaskTime(8)=32 and OnEventList(44)=1 | You have delayed the meeting about the pre-testing for too long and will have to face the consequences later!
48 | n |  | 1 |  | TaskTime(9)=6 | Your security officer advises that it would be a good idea to spend 2 days and £10k on security awareness training.
49 | y |  | 1 |  | ScoreSecurity<55 | Security is low and a hacker has exposed it by gaining access to the system using the password 'Let_Me_In' to cause malicious damage to files.
50 | y |  | 1 |  | TimeLag=1 | Your discussions with the security officer are fruitful and the outcome is the option of a more focused as well as shorter and cheaper training proposal of 1 day and £5k.
51 | n |  | 0 |  | TaskTime(14)=22 | Progress on task 14 is faster than expected.
52 | n |  | 1 |  | Time=230 | You hear that a security audit is to take place in a week's time.
53 | y |  | 1 |  | TimeLag=5 | The security auditor arrives and a favourable report is indicated.
54 | y |  | 1 |  | TimeLag=5 | During the security audit the security auditor compiles a long list of security weaknesses. Yo are obliged to pay £12k and spend 3 days strengthening your defences.
55 | y |  | 1 |  | TimeLag=5 | During the security audit the security auditor compiles a list of security weaknesses, together with recommendations for rectification.
56 | n |  | 0 |  | Time=1 | DEMONSTRATION EVENT for day 1, task 1. A sample of events will occur at various points in time. Select from options below to action your response.
57 | y | Redundant | 0 |  | Time=7 | DEMONSTRATION NOTE (Day 7). You can also click on the management initiative buttons to influence control of some aspects of the project.
58 | y | Redundant | 0 |  | Time=100 | Don't forget to keep an eye on the productivity tools available for purchase ...
76 | n |  | 1 |  | TaskTime(10)=4 | The Managing Director wants you to attend a two-day Business Information Technology seminar with her in Manchester.
77 | y |  | 1 |  | TaskTime(13)=2 | Top management support is low for the project. Rumour has it that this is due to the MD being upset that you declined to attend the conference in Manchester.
78 | y |  | 1 |  | TimeLag=3 | The conference was a great success. You have gained valuable top management support for the project and this rubs off on the clients.
79 | y |  | 1 |  | TaskTime(13)=5 | The MD expresses concern over the current progress of the project.
80 | y |  | 1 |  | TimeLag=2 | The MD attends a training session and is most impressed with the system. She increases your budget by £10,000 as a result!!
81 | y |  | 1 |  | TimeLag=1 AND Random<75 | The MD expressed her doubts at a board meeting. User managers were present and user acceptance is decreased.
82 | n |  | 1 |  | TaskTime(8)=37 AND ScoreMorale<55 | One of your project team has unexpectedly handed in her notice, saying she is not happy in the team.
83 | y |  | 0 |  | TimeLag=0 | The team member accepts the offer of a £2,000 bonus and morale is boosted as a consequence.
84 | y |  | 0 |  | TimeLag=0 | The unhappy team member leaves for a rival company. An equivalent of 2 days are lost on the project while a replacement is found, and morale drops as a result.
85 | y |  | 0 |  | TimeLag=3 | The unhappy team member returns from her 2 day break refreshed and has decided not to leave after all. Morale increases as a result of your caring management style.
86 | y |  | 0 |  | TimeLag=3 | The unhappy team member doesn't return from her 2 day break, and you lose 2 days whilst a replacement is found.
87 | n |  | 1 |  | TaskTime(3)=2 | During requirements analysis a team member suggests developing a small prototype, to assist with identifying user requirements.
88 | y |  | 1 |  | TimeLag=12 | Feedback from use of the prototype has enabled user requirements to be specified more precisely, and has pleased users who feel more involved in the project.
89 | y |  | 1 |  | TaskTime(8)=20 | The users requirements have changed, and they request that the system specification is changed to accomodate them during the programming task. Perhaps prototyping would have avoided this.
90 | n |  | 1 |  | TaskTime(4)=2 | A particular user interface requirement is causing real problems for your software designers
91 | y |  | 1 |  | TaskTime(13)=15 | Users notice that an important piece of interaction is missing from the system. This is due to the 'insignificant' interface requirement you omitted from the design earlier!
92 | y |  | 1 |  | TimeLag=0 | The users are not impressed with your suggestion to change their method of working, and insist the problem is rectified.
93 | y |  | 1 |  | TimeLag=4 | The users accept the interaction test, and are impressed with your user-oriented approach!
94 | y |  | 1 |  | TimeLag=1 | After careful discussion the users decide that the interaction requirement is not needed after all.
95 | y |  | 1 |  | TimeLag=1 | The users explain that the interaction is required to perform their work efficiently
96 | y |  | 1 |  | TimeLag=0 | The users are pleased that they are being involved in the project, and you gain their support as a result.
97 | y |  | 1 |  | TimeLag=0 | Your designers are not impressed with your 'iron hand' approach and morale suffers as a result. The interaction design changes take 3 days to complete but the users are satisfied.
98 | n |  | 1 |  | TaskTime(8)=5 | You come across a programmer who has used 2-digit year date fields on one of the screens. Where has he been since the Millenium?!
99 | y |  | 1 |  | TaskTime(10)=30 | During established 'Year 2000' date testing procedures the program falls over. The use of 2-digit year date fields is more widespread than you thought, and takes 5 days to rectify.
100 | y |  | 1 |  | TimeLag=3 | The use of 2-digit year date fields is more widespread than you thought: the audit shows that it will take an extra 2 days to rectify properly.
101 | y |  | 1 |  | TimeLag=2 | The 2-digit date problem must have just been an isolated oversight, there are no further problems.
102 | n |  | 1 |  | TaskTime(6)=8 | The new Web Server you ordered has failed to arrive.
103 | y |  | 1 |  | TimeLag=1 | The hardware fails to arrive and you've now lost a day on this task.
104 | y |  | 1 |  | TimeLag=0 | The Web server eventually turns up and the supplier is duly apologetic. That doesn't catch up on lost time but it's ok - the task is off the critical path!
105 | n |  | 1 |  | TaskTime(11)=15 | Maintenance crisis! Staff are required for urgent 'Euro Currency compliance' maintenance on a legacy system.
106 | n |  | 1 |  | TaskTime(8)=6 AND BoughtResource(3)=1 | Relational database flexibility gets you out of a development problem, and saves you 2 days as a result!
107 | n |  | 1 |  | TaskTime(14)=15 | Your company has merged with a competitor to increase market share. You need to re-evaluate the project requirements and allow for in the data conversion plan.
108 | y |  | 1 |  | TimeLag=2 | Re-evaluation of requirements suggests that the software will not run on the new merger partner's hardware. Perhaps you should have acquired open systems software.
109 | n |  | 1 |  | BoughtResource(7)=0 AND TaskTime(7)=5 | Your hardware supplier has just been liquidated. As you didn't invest in Open Systems software, spend 3 days migrating to new hardware.
110 | n |  | 1 |  | BoughtResource(8)=0 AND TaskTime(16)=32 | A fire in the operations centre results in the project being delayed for 4 days whilst recovery takes place.
111 | n |  | 1 |  | BoughtResource(8)=1 AND TaskTime(9)=8 | There is a fire in the operations centre, but because you have 'Hot Start' disaster recovery cover, the project will only be delayed by 1 day.
112 | n |  | 1 |  | TaskTime(11)=1 AND ScoreTime<50 | The project is running behind schedule.
113 | y |  | 1 |  | TaskTime(17)=5 | The system has crashed over 20 times in the first week of acceptance testing. You shouldn't have tried to save time on testing earlier.
114 | n |  | 0 |  | TaskTime(18)=0 AND ScoreAcceptance>55 | The users are very pleased with the system, although this still must be translated into business performance improvement to enjoy full success.
115 | n |  | 0 |  | TaskTime(18)=0 AND ScoreAcceptance<46 | The users aren't very pleased with the system at all. The chances are that they will decide not to use it, and stay with their current methods!
119 | n |  | 0 |  | TaskTime(11)=5 AND BoughtResource(6)=0 | A virus on the development machine results in a delay of 3 days to tidy up. Perhaps you ought to have updated your virus protection software.
120 | n |  | 1 |  | TaskTime(10)=15 | A task 9 testing engineer reports that a critical piece of code is vulnerable to very exceptional data conditions.
121 | y |  | 1 |  | TaskTime(18)=1 | The system crashes on the first day of live running! Apparently 'exceptional' data conditions happen frequently around here! User acceptance of the system takes a severe knock.
122 | y |  | 1 |  | TaskTime(17)=10 and ScoreQuality>57 | Your high quality user acceptance testing procedures picked up the vulnerable code issue. Users are disturbed, but partially re-assured since the system is not yet live.
123 | n |  | 1 |  | TaskTime(8)=20 AND TaskOvertime(8)<5 | Your HR manager is noticing signs of fatique amongst the programmers, who have been working long hours with little compensation from the company.
124 | y |  | 1 |  | TimeLag=2 | The programmers receive the bonus and are slightly happier for a while.
125 | y |  | 1 |  | TimeLag=2 | The programmers are grateful for the extra day's holiday each, and morale is increased as a result.
126 | y |  | 1 |  | TimeLag=2 | The programmers made the most of the party, and now seem a lot more relaxed at work! Morale increases.
127 | y |  | 1 |  | TaskTime(10)=2 | Sickness has increased amongst the programming staff, mostly due to stress. The project is delayed by 4 days as a result, and morale drops further still.
128 | n |  | 1 |  | TaskTime(8)=20 AND BoughtResource(1)=1 | The CASE tool allows part of system code to be generated automatically, saving you 3 days development time.
132 | n |  | 1 |  | TaskTime(8)=8 | One of the programmers has located some useful reusable modules are on an Internet user group, for the bargain price of £2,000.
133 | y |  | 1 |  | TimeLag=10 | The modules were downloaded from the Internet but unfortunately a virus was also downloaded with them! Maybe you ought to think about investing in some anti-virus software, even at this late stage?
137 | n | T | 1 | 80 | Time=80 | There are a limited number of places available on a training course to improve communications skills. The cost will be £2,000.
138 | y |  | 1 |  | TimeLag=5 AND (TaskState(17)=0 OR TaskTime(17)<30) | Places have become available on a training course for communication skills with a very reputable company. The cost will be £3,000.
139 | n |  | 1 |  | TaskTime(18)=1 | The project is now up and running, and another IT manager has asked for some of your developers for his new project.
140 | n |  | 1 |  | ResourceAvailable(4)=1 AND (TaskTime(1)>12 AND TaskTime(2)<10) | Hint: Do you think a formal approach to development could be a useful resource acquisition?
141 | n |  | 1 |  | TaskTime(4)=10 AND (ScoreQuality<55 AND BoughtResource(4)=0) | The organisation of the project is a bit of a shambles. Quality is suffering as a result. Maybe you should have thought about buying the Methodology earlier?
142 | y | naff | 1 |  | BoughtResource(5)=1 AND (TaskTime(10)=20 AND TaskOvertime(10)<5) | The reporting package you bought earlier was a shrewd investment! The flexibility of the package has speeded up testing of the software, saving you 5 days on this task.
143 | n |  | 1 |  | BoughtResource(5)=1 AND TaskTime(17)=20 | Due to the friendly user-interface of the reporting package you bought earlier, users are able to produce their own reports for testing! The users feel more involved; 3 days are saved and user acceptance increases.
144 | n |  | 1 |  | BoughtResource(1)=1 AND TaskTime(4)=12 | The use of CASE tools has saved time in producing design documentation.
145 | y | naff | 1 |  | BoughtResource(1)=1 AND (TaskTime(2)>1 AND TaskTime(3)<15) | The supplier of your CASE software has informed you that you are entitled to a 20% discount, as there was a special offer on at the time!
147 | n | W | 1 | 70 | Time=70 | During your tour of the office you notice that an argument has developed amongst the staff.
148 | y |  | 0 |  | TimeLag=1 | The meeting you called to thrash out disagreements has resulted in some great new ideas for the project! They will take an extra day to implement, but quality and morale are both increased.
149 | y |  | 0 |  | TimeLag=1 | Unfortunately the meeting to thrash out disagreements was not a success, and has resulted in the conflict developing further. Morale takes a tumble.
150 | n | W | 1 | 140 | Time=140 | You notice that your staff are all working extremely hard, and are gelling nicely as a team. They are beginning to work more efficiently and as a result 2 days are saved.
152 | n | Q | 1 | 80 | Time=80 | ISO 9000 auditors find a lack of procedures for documenting design changes.
154 | n | Q | 1 | 160 | Time=160 | Quality auditors recommend carrying out an audit of data to be converted to the new system.
155 | n | S | 1 | 40 | Time=40 | The security audit has expressed concern over your current security measures protecting your systems from unauthorised access via the Internet.
156 | y |  | 0 |  | TimeLag=7 | One of your IT support team, informs you that a hacker has penetrated your Internet security system, resulting in work being lost, and doubts are cast over the integrity of your data.
159 | n | U | 1 | 30 | Time=30 | During a user group meeting you discover that some of the users see the new system as a threat to their jobs, and are trying to influence others, to have the project scrapped.
161 | n | U | 1 | 110 | Time=110 AND ScoreTime>50 | Users seem impressed with the progress you've made so far, and are quite looking forward to using the system.
162 | n | H | 1 | 120 | Time=120 | You have a shortage of programmers with the required level of skill in Java, to carry out a particularly tricky task.
164 | n |  | 1 |  | TaskTime(1)=10 | You are contemplating carrying out a review of internal business processes.
165 | y |  | 1 |  | TimeLag=1 | The review of business processes presents you with an opportunity for streamlining the system, but how much can you take on at this stage?
167 | y |  | 1 |  | TaskTime(13)=15 | Due to the decision made earlier to change business processes, the time spent on training is increased by 3 days.
168 | n |  | 1 |  | TaskTime(7)=5 | Benchmark tests suggest that the old network may not be able to cope with estimated demand of the new software.
169 | y |  | 1 |  | TaskTime(17)=30 | Users are very impressed with the fast response time of the system. It was a good decision you made earlier to improve the network. User acceptance increases.
170 | y |  | 1 |  | TaskTime(17)=30 | Users are complaining that response times are too slow, and will be unmanageable when the system is live.
172 | n |  | 1 |  | TaskTime(3)=13 | One of your large suppliers has expressed an interest in linking your computer systems together to allow EDI trading to be permitted.
173 | y |  | 1 |  | TimeLag=5 | Two more suppliers express an interest in connecting to the new system.
174 | y |  | 1 |  | TimeLag=5 | Two more suppliers express an interest in connecting to the new system. Because you have carried out a full supply-chain audit you can assure them that connectivity is possible.
175 | y |  | 1 |  | TimeLag=0 AND ScoreSecurity<55 | Your suppliers are only willing to connect with the new system if your security measures are upgraded.
176 | y |  | 1 |  | TimeLag=2 | One of your largest suppliers are now refusing to supply you unless you are capable of trading via EDI. Your managers are furious with you, and insist that a full supply-chain audit is carried out.
179 | n |  | 1 |  | TaskTime(5)=20 | You need to decide what data will be used to test the software.
180 | n |  | 1 |  | TaskTime(4)=15 | One of the team suggests performing a design walkthrough to test the integrity of the design, and to stimulate possible new ideas.
181 | y |  | 1 |  | TimeLag=2 | It was a good decision to perform the design walkthrough. Some problems were uncovered, which would have delayed the project by 4 days later on.
182 | y |  | 1 |  | TaskTime(8)=15 | Inconsistencies in the design have been uncovered during programming, causing a delay of 4 days while the problem is rectified. Perhaps you should have performed a design walkthrough earlier!
183 | n |  | 1 |  | TaskTime(6)=2 | It is time to buy a Web server to run the new system on.
184 | y |  | 1 |  | TaskTime(17)=10 | Your new Web server crashed overnight, and you phone the supplier's support helpline. You finally get to speak to someone at 5.00pm and they promise to send someone out tomorrow.
185 | y |  | 1 |  | TimeLag=0 | The hardware supplier informs you that your support contract only entitles you to next day cover.
187 | n |  | 1 |  | TaskTime(12)=2 | You need to decide the structure of the training you will give to your users.
188 | y |  | 1 |  | TaskTime(17)=21 | Due to the inadequate training you gave the users, they are struggling to thoroughly test the system, and bugs are being overlooked! Quality decreases dramatically as a result.
189 | y |  | 1 |  | TaskTime(17)=21 | Due to the thorough training course you gave to the users, they are locating many obscure bugs in the software, and generating good feedback for the developers. Quality increases.
191 | n |  | 1 |  | TaskTime(12)=14 | Your operations staff need to be trained in day-to-day maintenance procedures, housekeeping and recovery procedures for the new system.
192 | y |  | 1 |  | TaskTime(18)=0 | Tomorrow the system is going live, and your support team still aren't up to speed on housekeeping and recovery procedures. Fingers crossed that nothing goes wrong!!
193 | y |  | 1 |  | TaskTime(13)=6 | Users are complaining about the lack of training they are receiving, and user acceptance falls dramatically as a result.
194 | y |  | 1 |  | TaskTime(13)=6 | Users are pleased with the quality and amount of time being spent to train them. User acceptance increases as a result.
195 | n |  | 1 |  | TaskTime(16)=13 | One of your team suggests carrying out a pilot implementation of the system, towards the end of the acceptance testing stage, involving a small subset of users.
196 | y |  | 1 |  | TaskTime(17)=20 | The users involved in the pilot implementation have become very enthusiastic about the system, and this in turn motivates other users.
197 | n |  | 0 |  | TaskTime(16)=30 | You need to decide how you are actually going to deploy the system.
198 | y |  | 0 |  | TaskTime(18)=0 | The users are pleased to have Phase I functionality, but are anxious to gain the full system as quickly as possible, to improve the service level provided to customers.
199 | y |  | 0 |  | TaskTime(17)=45 | Running the old and new systems in parallel is putting a real strain on your resources. Overtime must be paid, at a cost of £3,000 to keep the project on schedule.
200 | n |  | 1 |  | TaskTime(9)=1 | System documentation must be prepared, so you need to adopt a strategy to achieve this, efficiently but accurately.
201 | n |  | 1 |  | TaskTime(9)=5 | A decision has to be made about the form of user documentation which is to be produced.
202 | n |  | 1 |  | TaskTime(9)=10 | One of the team comes up with an idea to use a select set of users to produce the documentation themselves.
203 | y |  | 1 |  | TaskTime(17)=15 | Users are not happy with the form of documentation provided, and the acceptance testing is in danger of falling behind schedule as a result.
204 | y |  | 1 |  | TimeLag=1 | Acceptance testing is delayed by 2 days as a result of poor user documentation!
210 | y |  | 1 |  | TaskTime(11)=10 | System testing goes smoothly as in-house staff have a good knowledge of system documentation. You save 2 days on the task as a result.
211 | y |  | 1 |  | TaskTime(11)=10 | System testing is held up for 2 days as in-house staff do not understand system documentation. Maybe you should have included them in preparing the documentation earlier!
212 | n |  | 1 |  | TaskTime(14)=6 | You are trying to decide whether to split the data conversion into phases to decrease risk, but haven't finalised the details yet.
213 | y |  | 1 |  | TaskTime(17)=4 | Users discover that the data has not been converted correctly! You shouldn't have reduced the conversion testing earlier! User acceptance also falls.
214 | y |  | 1 |  | TaskTime(15)=10 | Your programmers are having real problems converting the historical data as requested by users. The mapping rules to the new format turn out to be very complex.
215 | y |  | 1 |  | TimeLag=2 | The users decide that the very old historical data will not be required after all.
216 | y |  | 1 |  | TimeLag=2 | It was a good job you didn't discard the historical data from the conversion. The users say that this data is essential for management reporting purposes.
219 | n |  | 1 |  | TaskTime(14)=10 | During conversion testing a user informs you that she requires some historical data to be in the new system, which is not easily accessible in the old database structure.
220 | n |  | 1 |  | TaskTime(13)=10 AND ScoreSecurity<55 | On of your team reports that he has noticed other members of staff letting people into the building through the security door without checking ID.
221 | n |  | 1 |  | TaskTime(13)=2 | One of your team who was working late last night, thought he saw somebody snooping around outside the building.
222 | y |  | 0 |  | TaskTime(18)=1 | Your 'cut and run' implementation was risky and bugs found under live conditions cause users to lose some confidence and 2 days' hurried re-work during task 18.
223 | y |  | 1 |  | TimeLag=1 | You have let security lapse too far; this time you find intruders have stolen equipment - but the data on it was far more valuable.
300 | n | R | 1 |  | TaskTime(2)=3 | Opportunity to train the team in a leading web applications development methodology on 2-day course.
301 | n | R | 1 |  | TaskTime(3)=3 | Opportunity to buy a Computer-Aided software engineering tool for £10k.
302 | n | R | 1 |  | TaskTime(4)=5 | Opportunity to select a Relational Database Management System as a key element of the design architecture.
303 | n | R | 1 |  | TaskTime(4)=15 | Opportunity to buy a Report writer that will allow end-users to create their own data output on demand for Acceptance testing in task 17.
304 | n | R | 0 |  | TaskTime(3)=5 | Opportunity to renew your virus checking software for the development machines to the latest professional standard for £8k.
305 | n | R | 1 |  | TaskTime(4)=12 | Choose open source software with a support contract for £8k
306 | n | R | 1 |  | TaskTime(1)=8 | Take out a 'Hot-Start' Disaster Recovery agreement for £6k to protect your development centre in case of serious accident.