## First Sheet
EventID | OptionID | Description | If | Then | Else | Comment
1 | 1 | Review the project's morale performance. |  |  |  | Just a warning!
2 | 1 | Review the project's morale performance. |  |  |  | Just a warning!
3 | 1 | Check the project's time performance. |  |  |  | Just a warning!
4 | 1 | Check the project's time performance. |  |  |  | Just a warning!
5 | 1 | Review the project's cost performance. |  |  |  | Just a warning!
6 | 1 | Review the project's cost performance. |  |  |  | Just a warning!
7 | 1 | Check the project's user acceptance level. |  |  |  | Just a warning!
8 | 1 | Check the project's user acceptance level. |  |  |  | Just a warning!
9 | 1 | Check the project's technical quality. |  |  |  | Just a warning!
10 | 1 | Check the project's technical quality. |  |  |  | Just a warning!
11 | 1 | Check the project's security arrangements. |  |  |  | Just a warning!
12 | 1 | Check the project's security arrangements. |  |  |  | Just a warning!
13 | 1 | Continue
14 | 1 | Take the opportunity |  | ProjectDelay(2) CurrTaskQual(1) |  | A good way to trade time for quality.
14 | 2 | You believe that quality is satisfactory; continue work as normal. |  |  |  | Fair move if time is of the essence and quality is already reasonable.
16 | 1 | Have a quiet word with the programming team leader. | Random<50 | TaskQuality(8,-2) Event(17) | Event(18) | This was sensitive but unlikely to solve the problem in this instance.
16 | 2 | Interview the programmers and offer them counselling. | Random<75 | TaskQuality(8,-2) Event(17) | Event(18) | This was sensitive but unlikely to solve the problem in this instance.
16 | 3 | Hold a full project meeting and explain that this behaviour is unacceptable. It will surely cost a day's work but should push the message home. |  | TaskDelay(8,1) ScoreMorale(-1) TaskQuality(8,2) Event(18) |  | This was a firm but effective response..
16 | 4 | Adopt a wait and see approach |  | Event(17) TaskQuality(8,-2)
17 | 1 | Hold a full project meeting and explain that this behaviour is unacceptable. It will surely cost a day's work but should push the message home. Better late than never. | Random<75 | TaskQuality(8,2) ScoreMorale(-2) ProjectDelay(1) Event(18) | Event(17) TaskQuality(8,-1) | This was a firm but effective response..
17 | 2 | You must find an opportunity to have a serious word with the programming team leader about this issue. |  | Event(17) TaskQuality(8,-1) |  | Very weak management of this issue.
17 | 3 | Dismiss the programmers responsible. |  | ScoreMorale(-1) Event(18) |  | A firm but effective response.
18 | 1 | Continue
21 | 1 | You take the view that the overtime cost of £5k to catch up lost time will be worth the boost to the project team's morale. |  | TaskCost(17,5) ScoreMorale(2) |  | Sensible move if you could afford it.
21 | 2 | E-mail back to say you had better concentrate on maintaining progress. |  | ScoreMorale(-1) |  | A task-oriented approach which loses the opportunity to maintain relationships.
22 | 1 | What sort of sucker do they take you for? This is a test of your firmness and you should turn down the request forthwith. |  | Event(23) TaskQuality(10,-2) ScoreMorale(-2) |  | This was a reasonable request considering the stress of the testing phase.
22 | 2 | She asked very politely and hinted that some staff are taking this time unofficially anyway. Accept the request and make a virtue out of it. |  | Event(24) TaskQuality(10,2) ScoreMorale(2) |  | A wise move.
22 | 3 | Dismiss the request and start checking the break times taken. |  | Event(23) TaskQuality(10,-3) ScoreMorale(-3) |  | This response was harsh by any standards and unlikely to pay off.
23 | 1 | Continue. |  |  |  | Well what did you expect?
24 | 1 | Continue. |  | TaskDelay(10,-3) |  | Your intelligent response paid off.
27 | 1 | Rumours can be damaging to morale. Hold a project meeting to 'replace rumours with facts'. The cost of disruption will be £4k. |  | Event(28) ProjectCost(4) ScoreMorale(1) |  | The disruption was worth it to dispel the rumours and their damaging effect on productivity.
27 | 2 | Rumours are a fact of life in this sort of job. A bit of uncertainty will keep the staff on their toes. |  | Event(29) TaskQuality(4,-1) ScoreMorale(-2) |  | Yes but also creates stress and lower productivity.
28 | 1 | Continue.
29 | 1 | Looks like you'll have to call the project meeting after all. Better spend another £5k by enlisting the help of your company's PR team! |  | Event(28) ProjectCost(5) |  | Better late than never!
29 | 2 | Ignore the rumours - they are a nuisance but will go away in time. | Random<80 | Event(29) TaskQuality(4,-1) ScoreMorale(-2) | Event(30) | They might go away, but then again ...
29 | 3 | Write a letter to all staff dismissing the rumours. | Random<40 | Event(29) TaskQuality(4,-1) ScoreMorale(-2) | Event(30) | This approach is unlikely to gain the confidence of your staff.
30 | 1 | Continue.
31 | 1 | Put up a notice making it clear that you are expecting a full week's work despite the conditions. |  | Event(32) TaskQuality(2,-1) ScoreMorale(-2) |  | This option reduced quality and morale and caused the team to confront you.
31 | 2 | Meet the project team at the door and offer them two days off without loss of salary. |  | TaskDelay(2,2) ScoreMorale(1) |  | This made the team happy but you lost 2 days on a critical task.
31 | 3 | Take no action: wait and see if the team complains. |  | Event(32) |  | Of course the team complained!
32 | 1 | Accept that realistically it is not worth pursuing work. Make it look like you are doing the team a favour. |  | ScoreMorale(2) TaskDelay(2,2) TaskQuality(2,1) |  | This cost 2 days but increased morale and quality.
32 | 2 | Refuse the request and tell the team to work on regardless to make some early progress. |  | Event(33) ScoreMorale(-2) TaskQuality(2,-1) |  | Rather a hard line decision which decreased quality, morale and precipitated a confrontation.
32 | 3 | Refuse the request but send for a fleet of industrial fan heaters to make work just about possible: this will cost £1k. |  | TaskCost(2,1) TaskQuality(2,-1) ScoreMorale(-1) |  | A true compromise which maintained progress but at the expense of cost, quality and morale.
33 | 1 | Back down whilst you have the change and pay let the team off work for two days. |  | TaskQuality(2,1) ScoreMorale(1) TaskDelay(2,2) |  | A blow to your pride but a safe decision for the project, with a delay but an increase in quality and morale.
33 | 2 | Call their bluff and see whether they mean it. | Random<30 OR TaskTime(1)>35 | Event(34) | Event(35) | A risk which either brought the contractor into line or precipitated a walk-out ...
34 | 1 | Continue. |  |  |  | You were lucky!
35 | 1 | No other option! |  | TaskDelay(2,4) ScoreMorale(-2) |  | Unlucky result but you precipitated the confrontation!
36 | 1 | This must be an old test routine. Tell the programmers to delete it. |  | Event(37) |  | This action was asking for trouble! ...
36 | 2 | Suspend the work on this routine to investigate. It will cost £2k in contractor fees and a day to catch up. |  | Event(38) TaskCost(15,2) TaskDelay(15,1) |  | This wise decision prevented serious data corruption.
37 | 1 | Test data has been lost and needs to be re-created. It will cost you 3 days in task 15 and £3k. |  | TaskDelay(15,3) TaskCost(15,3) |  | Let's hope your own documentation is to a higher standard, also that your project leadership becomes more circumspect!
38 | 1 | Continue. |  |  |  | Or was it a lucky guess?
39 | 1 | Insist on immediate replacement. It will delay task 6 by 5 days, but you know there is heavy work ahead for this kit. Claim £5k compensation back from the supplier. |  | TaskDelay(6,4) ProjectCost(-5) |  | A wise move to save problems later, especially if the task was not on the critical path.
39 | 2 | The machine which came is a smarter blue than the one ordered and there's a good safety margin built into your estimates. It will do. |  | Event(40) |  | A foolish move; you paid for it when the machine crashed out under heavy initial transaction loads.
40 | 1 | Users are unhappy, 4 days are lost on a critical task and the business will charge the project for the losses. |  | ProjectCost(10) ProjectDelay(4) |  | This was to be expected!
41 | 1 | Take an extra 3 days in task 8 and spend £5k to do this; that's what the quality manager is there for. |  | Event(42) TaskDelay(8,3) TaskCost(8,5) ScoreMorale(-1) |  | The cost will have been worth it in the end.
41 | 2 | Pre-testing was not in the plan and your team will not be keen on this intervention. Stick to the plan. |  | Event(43) |  | A short term saving but your quality manager is there for a reason and you will see the results later.
41 | 3 | Seek a meeting with the quality manager to discuss the problem. |  | Event(44) |  | A good idea, but did the meeting ever happen?
42 | 1 | What a waste of a week! Ignore the looks and make some much-needed progress. |  | Event(43) |  | A mistake to ignore your chosen quality manager's advice - and you saw the results later.
42 | 2 | Insist on further upsetting the team by re-working the core modules. Task 8 will take a further 2 days. |  | TaskDelay(8,2) TaskQuality(8,2) ScoreMorale(-1) |  | A brave move which will pay off by increasing quality despite loss of time and morale.
43 | 1 | You have to spend 6 days re-working the core module data definitions and tracing through to the other modules. |  | TaskDelay(10,6) TaskQuality(10,1) |  | The only good result was a slight restoration of quality. But you should have addressed this problem earlier when you were advised by the quality manager.
44 | 1 | It's a busy afternoon and this is not exactly top priority; defer in your diary for another week. |  | Event(44) |  | Your diary faithfully prompted you in 5 days ...
44 | 2 | The quality manager is stalling because she is also busy; press for a meeting tomorrow which will cost a day's progress to programming. | Random<75 | TaskDelay(8,1) Event(45) | Event(46) | The meeting may happen or it may not ...
44 | 3 | Cross this item off your long To-Do list. |  | Event(43) |  | This negligent management was sure to result in problems later ...
45 | 1 | Accept the recommendation. |  | Event(42) TaskDelay(8,2) TaskCost(8,2) |  | A useful compromise although the result of the test still presented problems.
45 | 2 | Reject this compromise and insist on a full test taking 3 days and costing £5k. |  | Event(42) TaskDelay(8,3) TaskCost(8,5) ScoreMorale(-2) |  | Your response lost morale as well as the tangible costs.
46 | 1 | Go ahead with the pre- testing anyway - you must be seen to be in control. |  | Event(42) TaskDelay(7,3) TaskCost(7,5) ScoreMorale(-3) |  | This stance sapped morale but at least disovered the problems early.
46 | 2 | Accept the team's view and let their work speak for itself. |  | Event(43) |  | The work did speak for itself - it was bad, and resulted in knock-on problems later.
47 | 1 | Continue - but watch this space! |  | Event(43) CancelEvent(44) |  | This gross mismanagement caused a data corruption problem in the core module.
48 | 1 | You believe that security is adequate and the security officer has no sense of urgency about project completion. Continue work as normal. |  | Event(49) |  | This was asking for trouble unless your security score was high.
48 | 2 | Accept the recommendation. |  | ProjectDelay(2) ScoreSecurity(2) ProjectCost(10) |  | A safe decision which increased security and avoided a nasty incident of hacking.
48 | 3 | You take the point but can't afford the delay, so spend £5k on some glossy 'security starts here' educational multimedia presentations for staff. |  | Event(49) ProjectCost(5) |  | Unfortunately for you this was interpreted as an ineffectual escape from responsibility, and a nasty hacking incident followed.
48 | 4 | Spend the day talking through the issues with the security officer and helping plan the training. The opportunity cost of your time is £2k! |  | ProjectCost(2) Event(50) |  | This led to a more palatable solution being negotiated.
49 | 1 | It takes 3 full days and costs £20k to rectify the damage. |  | ProjectDelay(3) ProjectCost(20) ScoreSecurity(2) |  | Security was recovered slightly but at a high cost, not least to your professional reputation.
50 | 1 | The security officer still has no sense of urgency. Insist on continuing work as normal. |  | Event(49) ScoreSecurity(-3) |  | This response was asking for trouble unless your security score was high.
50 | 2 | Accept the recommendation and use the time to plan and to boost morale. |  | ProjectCost(5) ProjectDelay(1) ScoreMorale(1) ScoreSecurity(2) |  | This was a good compromise with less delay and cost, and an increase to morale and security.
51 | 1 | One of the best bits of news you've had! However the effect of the 8 days saving seems less than you would expect ... WHY? |  | TaskDelay(14,-8) |  | Since task 14 was non-critical, the saving did not translate into overall project performance improvement.
52 | 1 | Spend that week effectively at 60% speed on all tasks, monitoring and enforcing standard security procedures. Spend £10k on checking security routines. | ScoreSecurity>51 | Event(53) ProjectCost(10) ProjectDelay(3) ScoreSecurity(3) | Event(55) ProjectCost(10) ProjectDelay(3) ScoreSecurity(3) | Increased security at the expense of time and money.
52 | 2 | You are confident that your security is up to scratch and you have nothing to fear from the inspection. | ScoreSecurity<55 | Event(54) ScoreSecurity(-1) | Event(53) | Lost some security and risked a bad report unless security was 55% or over.
53 | 1 | Congratulations, but keep up the high standards - the inspector can return at short notice. |  |  |  | No further comment.
54 | 1 | A stitch in time saves nine. |  | ProjectCost(12) ProjectDelay(3) ScoreSecurity(3)
55 | 1 | You'd better follow up and implement the recommendations at a cost of 1 day and £10k. |  | ProjectDelay(1) ProjectCost(10) ScoreSecurity(2) |  | Good move to correct clear weaknesses.
56 | 1 | Option 1. For demonstration only, this will increase morale by one point. |  | ScoreMorale(1) |  | Demonstration only
56 | 2 | Response 2. For demonstration only, this will increase security by one point. |  | ScoreSecurity(1) |  | Demonstration only
57 | 1 | Continue
58 | 1 | Continue, then inspect the management resources.
76 | 1 | You're far too busy at the moment with organising the integration testing. Make up a good excuse and politely decline the request. |  | Event(77) |  | Missed an opportunity to gain top management support for the project
76 | 2 | Take the trip to sunny Manchester and delay the project by 2 days. |  | Event(78) ProjectDelay(2) |  | Smart move, the short-term loss of 2 days is more than made up for by the top management support gained for the project.
77 | 1 | You'll have to look out for other opportunities to make amends! | Random<60 | Event(79) |  | If you were unlucky this response generated further concern from the MD.
78 | 1 | Continue |  | ScoreAcceptance(2) |  | User Acceptance is increased.
79 | 1 | Ignore him, he's always interfering. |  | Event(81) |  | A doubtful response.
79 | 2 | Invite the MD to attend a training session to suppress his fears |  | Event(80) |  | Good move. You need top management support to have a successful project.
79 | 3 | Send him an e-mail and tell him everything is fine. |  | ScoreAcceptance(-1) |  | Missed opportunity to gain management support.
80 | 1 | That extra cash should come in handy! |  | ScoreAcceptance(1) Budget(10) |  | Increased budget and user acceptance.
81 | 1 | Continue |  | ScoreAcceptance(-2) |  | Keep the MD 'on side' for if (when) the going gets rough!
82 | 1 | She's a valuable team member so offer her a £2k bonus to stay to completion. | Random<50 | Event(83) | Event(84) | A fair offer but a toss-up whether she accepted.
82 | 2 | Show her the door. IT staff are two-a-penny these days, you'll replace her soon enough. |  | Event(84) |  | This is a loss to the team and to your project timescale.
82 | 3 | It's been a busy time for her recently. Tell her to take 2 days leave, paid by the firm, to rest and contemplate her decision, at a cost of £1k to the firm. | Random<80 | Event(85) ProjectCost(1) | Event(86) ProjectCost(1) | A considerate response which should solve the problem if you were lucky.
83 | 1 | Continue |  | ProjectCost(2) ScoreMorale(1) |  | Costs are incurred but morale is increased
84 | 1 | Continue |  | ProjectDelay(2) ScoreMorale(-1) |  | A good team member is well worth keeping. £2k would have been a small price to pay.
85 | 1 | Continue |  | ScoreMorale(2) |  | Costs are incurred, but disruption would have been much greater if a valued team member had left the project.
86 | 1 | Continue |  | ProjectDelay(2) |  | An unlucky result for you - at least you tried your best.
87 | 1 | Develop the prototype at a cost of £10k. |  | Event(88) TaskCost(3,10) |  | Prototypes increase technical quality due to the more precise specification of requirements.
87 | 2 | Dismiss the idea, as the system requirements seem pretty clear for this type of project. |  | ScoreAcceptance(-2) TaskQuality(3,-2) Event(89) |  | Both technical quality and user acceptance suffer as a result.
88 | 1 | Continue |  | TaskQuality(3,2) ScoreAcceptance(2) |  | Technical quality and user acceptance are increased.
89 | 1 | Re-analyse the requirements, change the design and re-implement the changes required, delaying the project by 5 days. |  | TaskDelay(8,5) TaskQuality(8,3) |  | Even though days are lost, in the long-term technical quality is improved.
89 | 2 | Ignore the request as the specification is frozen, and further delays will put the project deadline in jeopardy. |  | TaskQuality(8,-2) ScoreAcceptance(-2) |  | How useful is a poorly specified system, even if it is delivered on time? It probably won't be used!
89 | 3 | Inform users that the requirement changes are all appropriate, but due to time constraints, they will be included in a later release of the software |  | ScoreAcceptance(-1) TaskQuality(8,-1) |  | A phased approach can be appropriate when deadlines are tight and users can wait for additional functionality. For the first release technical quality will be reduced.
90 | 1 | It is only a minor requirement, just leave it out of the design. |  | Event(91) |  | It might be worth investigating the importance first!
90 | 2 | Discuss the importance of the requirement with the users and designers. | Random<30 | Event(94) | Event(95) | The chances were that the users would still need the requirement to be included.
90 | 3 | Tell your designers to pull their fingers out and solve the problem. They're being paid enough! |  | Event(97)
91 | 1 | Try to persuade the users that the interaction is not needed. |  | Event(92) |  | Isn't it about time you listened to your users?
91 | 2 | Suggest an alternative method of interaction, which the current system performs but is slightly more time consuming for users. | Random<65 | Event(92) | Event(94) | It is possible that users might accept the change.
91 | 3 | Spend an extra 2 days incorporating the change into the software. |  | TaskDelay(13,2) Event(93) |  | You shouldn't have ignored the problem earlier, it will always cost more to fix the problem later on.
92 | 1 | You have no choice but to rectify the problem, delaying the project by 3 days. As a result user acceptance also takes a knock. |  | ProjectDelay(3) ScoreAcceptance(-2) |  | You shouldn't have ignored the problem earlier, it will usually cost more to fix the problem later on.
93 | 1 | Continue |  | ScoreAcceptance(2) |  | No further comment.
94 | 1 | Continue |  |  |  | It is always worth talking to the users. Sometimes requirements are overspecified initially.
95 | 1 | Instruct the designers to incorporate the interaction into the design, delaying the task by 2 days. |  | TaskDelay(4,2) ScoreAcceptance(2) |  | Your clients were happy with direct response.
95 | 2 | Ask the users to relay their requirements directly to the designers, so that an agreeable compromise can be implemented. |  | Event(96) TaskDelay(4,1) |  | OK but a direct response might impress the users more.
96 | 1 | Continue |  | ScoreAcceptance(1) |  | It is a good idea to involve users as much as possible in the project, as the software is more likely to be used when live.
97 | 1 | Continue |  | TaskDelay(4,3) ScoreMorale(-3) ScoreAcceptance(1) |  | Maybe you need to be a bit more diplomatic with your staff!
98 | 1 | You know that he's a good programmer, and it's just an oversight. Point out the mistake and ask him to change the year field to 4-digits. |  | Event(99) TaskQuality(8,-2) |  | Have you not heard of the seriousness of the 'Year 2000' bug?
98 | 2 | Spend a day performing an audit of the programmer's code, to ensure the problem isn't more widespread. | Random<50 | Event(100) TaskDelay(8,1) TaskQuality(8,1) | Event(101) TaskDelay(8,1) TaskQuality(8,1) | The initial delay may well save you time in the long run if the problem is more widespread.
98 | 3 | Spend 2 days performing an audit of all code, and reminding users of the seriousness of the 'Year 2000' bug. |  | Event(100) TaskDelay(8,2) TaskQuality(8,3) |  | The initial delay may well save you time in the long run if the problem is more widespread.
99 | 1 | Continue |  | TaskDelay(10,5) |  | An audit earlier on would have saved time in the long-run.
100 | 1 | Leave the problem for now - you can pick it up later if it really proves necessary. |  | Event(99) |  | This took you longer in the long run: 'a stitch in time saves nine'.
100 | 2 | Spend the extra 2 days rectifying the problem during integration testing. |  | TaskDelay(10,2) TaskQuality(10,1) |  | Good judgement to address the problem as it would have taken longer to fix later on: 'a stitch in time saves nine'!
101 | 1 | Continue |  |  |  | Lucky you! It is better to be safe than sorry!
102 | 1 | Wait. The new hardware will probably turn up shortly. |  | Event(103) TaskDelay(6,1) |  | You could afford the delay on this non-critical-path task.
102 | 2 | Replace the supplier, resulting in a delay of 2 days while the server is delivered, and an additional cost of £2k. |  | TaskDelay(6,2) TaskCost(6,2) |  | It might have been worth ringing the supplier first.
102 | 3 | Phone the supplier and give them some grief! | Random<67 | Event(103) TaskDelay(6,1) | Event(104) | You may have been lucky with a positive response ...
103 | 1 | Replace the supplier, resulting in a delay of 1 day while the server is delivered, and an additional cost of £2k. |  | TaskDelay(6,1) TaskCost(6,2) |  | Reasonable response but If you had persisted the supplier would have turned up eventually.
103 | 2 | Phone the supplier and give them some grief! | Random<34 | Event(103) TaskDelay(6,1) | Event(104) | Time is not critical on this task.
104 | 1 | Continue
105 | 1 | You've no choice but to let the staff go, delaying the project by two days. |  | ProjectDelay(2) |  | These events are sent to try us!
106 | 1 | Continue |  | TaskDelay(8,-2) |  | The relational database proved a useful acquisition.
107 | 1 | You have no choice but to spend a day re-evaluating! | BoughtResource(7)=1 | ProjectDelay(1) | ProjectDelay(1) Event(108) | Open Systems Conformance makes this type of nightmare easier to cope with, so if you took this option you at least avoided a worse delay later.
108 | 1 | You need to adapt software delaying the project by 2 days. Continue. |  | ProjectDelay(2) |  | You should have paid extra earlier on to ensure your hardware conformed to Open Systems standards.
109 | 1 | You have no choice but to take the time But does it matter? |  | TaskDelay(7,3) |  | Open Systems software can be helpful but it depends what activities it might affect.
110 | 1 | You should have bought disaster recovery services. A 'Hot start' would have had you up and running again with minimal disruption. |  | ProjectDelay(4) |  | The need for disaster recovery cover is often overlooked by organisations.
111 | 1 | Continue |  | ProjectDelay(1) |  | The delay to the project would have been much more significant had you not bought the disaster recovery cover.
112 | 1 | Reduce testing to a bare minimum to save 5 days on this task. |  | TaskDelay(11,-5) TaskQuality(11,-3) Event(113) |  | If you scrimp on testing, technical quality will inevitably suffer as a result.
112 | 2 | Carry on as originally planned. |  |  |  | Very wise! Never scrimp on testing, it is essential!
113 | 1 | You have no choice but to delay the project by 4 days while intensive system testing and rework is carried out. |  | ProjectDelay(4) |  | A salutory experience of nipping problems in the bud.
114 | 1 | Continue
115 | 1 | Continue |  |  |  | Even a technically perfect system may not be accepted by the users.
119 | 1 | Continue |  | TaskDelay(11,3) ScoreSecurity(-2) |  | It would have been wise to update your anti-virus software.
120 | 1 | Overall you believe that quality is reasonable and the chance of these conditions occurring is very low. Ignore this report. |  | Event(121) CurrTaskQual(-2) |  | Reduces quality. Have you heard of "Murphy's Law"?
120 | 2 | Leave it for now, you'll pick this up later during routine acceptance testing. |  | Event(122) Event(121) |  | Was your quality high enough to remember this issue?
120 | 3 | Delay the task for 2 days while the problem is investigated and fixed. |  | TaskQuality(10,2) TaskDelay(10,2) |  | A trade-off between time and quality. Which is more important?
121 | 1 | Spend a 2 days, one night and £4k to fix the problem and patch up your reputation. |  | ScoreAcceptance(-3) |  | That will teach you to sweep problems under the carpet or depend on low quality testing procedures! If it can go wrong, it will (Murphy)!
122 | 1 | A couple of days will solve this problem once and for all. |  | TaskDelay(17,2) CancelEvent(121) ScoreAcceptance(-1) |  | Good job your quality procedures were up to scratch.
122 | 2 | Overall you believe that quality is reasonable and the chance of these conditions occurring is very low. Ignore this issue. |  |  |  | If it can go wrong, it will (Murphy)! You missed your chance to prevent an embarrassing crash of the live system.
123 | 1 | Offer each programmer a one-off bonus, costing a total of £5,000. |  | Event(124) |  | Morale is very important for the smooth running of a project.
123 | 2 | Offer them a day off each in lieu, resulting in the project being delayed by 2 days. |  | Event(125) |  | Morale is very important for the smooth running of a project.
123 | 3 | Organise a staff social event, to thank the workers for their effort costing, £5,000. |  | TaskCost(8,5) Event(126) |  | Often it is just recognition of effort that is needed to boost morale!
123 | 4 | Carry on as usual, no programmer has officially complained. |  | Event(127) |  | Bad move, morale is very important for the smooth running of a project.
124 | 1 | Continue |  | TaskCost(8,5) ScoreMorale(2) |  | A social event or break would have had a greater effect on morale.
125 | 1 | Continue |  | ProjectDelay(2) ScoreMorale(2) |  | A day off can generate a lot of goodwill and a refreshed attitude.
126 | 1 | Continue |  | ScoreMorale(2) |  | You took a good opportunity to raise the team spirits.
127 | 1 | Continue |  | ScoreMorale(-1) TaskDelay(10,4) |  | This is the result of programmers working too many hours without recognition.
128 | 1 | Continue |  | TaskDelay(8,-3) |  | It was a smart move buying the 4GL licence.
132 | 1 | They look like they're exactly what you're after, and will save you 2 days work. | BoughtResource(6)=1 | TaskDelay(8,-2) TaskCost(8,2) | TaskDelay(8,-2) TaskCost(8,2) Event(133) | A useful move as long as you have virus protection mechanisms in place.
132 | 2 | Develop them in-house, as it will be good practice for your programmers. |  | ScoreSecurity(2) |  | Good for security, as it is possible a virus could have been downloaded with the modules.
133 | 1 | You have no choice, but to restore the development system, delaying the project by 3 days. |  | ProjectDelay(3) |  | You should have invested in an anti-virus licence.
137 | 1 | Send a selection of your development team on the course. The training may come in handy later. |  | ScoreMorale(2) ProjectCost(2) |  | Morale increases.
137 | 2 | You're unsure about the quality of the training provided by this company. Wait a while and send your developers on a course with a more reputable training company. |  | Event(138) |  | Luckily a better course comes up.
138 | 1 | Send a selection of your developers on the course. |  | CurrTaskQual(1) ProjectCost(3) |  | A sound investment for quality.
138 | 2 | Decide against the training, communication skills is just common sense anyway. |  | ScoreMorale(-1) |  | Morale is reduced. The training might have helped to increased coordination with the users.
139 | 1 | Agree, as they do not have the correct skills for your next project anyway. |  | ScoreAcceptance(-1) |  | User acceptance took a final plunge since users have no expert support!
139 | 2 | Tell the manager that he can have the developers in 2 months time. You need them to man the helpdesk while the system is being introduced. |  | ScoreAcceptance(2) |  | A final boost to user acceptance!
140 | 1 | Continue |  |  |  | A hint, to lead you into buying the Methodology resource!
141 | 1 | It's too late to buy the 'Methodology' resource. Look for other opportunities to maintain quality. |  | TaskQuality(4,-3) |  | A formal methodology for development projects can increase the quality of the project.
142 | 1 | Continue |  | TaskDelay(10,-5) |  | Reports are much quicker to produce using a package than through hard-coding reports. But did the 5 days saving count towards the project time?
143 | 1 | The time saving is welcome, and users are happy: continue. |  | ScoreAcceptance(2) TaskDelay(17,-3) |  | The users like to feel involved in the project, and 3 days are also saved.
144 | 1 | Deploy this tool to save 3 days on system design. |  | TaskDelay(4,-3) |  | UpperCASE tools automate much of the software design process.
145 | 1 | Continue |  | ProjectCost(-2) |  | Looks like you bought at the right time! That was a stroke of luck!
147 | 1 | Ignore them, it's just workers letting off a bit of steam. |  | ScoreMorale(-2) |  | Team morale suffers as a result of your negligent approach.
147 | 2 | If harnessed correctly, conflict can be a good way to stimulate new ideas. Call a meeting to thrash out the conflicting opinions. | Random<75 | Event(148) | Event(149) | The chances are this will result in some great new ideas for the project.
147 | 3 | Call a staff meeting, and make it perfectly clear that this sort of behaviour will not be tolerated! |  | ScoreMorale(-2) |  | Morale suffers as a result of your stand-off attitude.
148 | 1 | Continue |  | ProjectDelay(1) ScoreMorale(3) CurrTaskQual(1)
149 | 1 | Look out for chances to improve morale in the future. |  | ScoreMorale(-1) |  | Unlucky outcome; morale was reduced slightly but at least you tried!
150 | 1 | Organise a team 'Paintball' event and party at the weekend, as a reward to staff, and to enhance the team approach. Total cost: £1,000. |  | ScoreMorale(2) ProjectDelay(-2) ProjectCost(1) |  | Morale is also increased.
150 | 2 | No need to do anything, all is well! |  | ProjectDelay(-2) |  | Missed an opportunity to increase morale.
152 | 1 | You must pay £3,000 on staff training, but the system design quality of increases as a result. |  | ProjectCost(3) TaskQuality(4,3)
154 | 1 | Carry out the audit. It will delay the project by 2 days, but it's better to be safe than sorry! |  | TaskQuality(14,3) ProjectDelay(2) |  | Technical quality increased.
154 | 2 | No need to bother, you're confident that your current approach to data conversion is sufficient. | Random<70 | TaskQuality(14,-2) |  | Technical quality was likely to suffer as a result.
155 | 1 | Invest £3,000 in installing a fail-safe "Firewall" protection system. |  | ProjectCost(3) ScoreSecurity(2) |  | Security is increased. The "Firewall" will prevent hackers accessing your internal systems, but will not ensure that credit card payments over the Internet are not intercepted.
155 | 2 | There have been no reported security breaches so far, it shouldn't be a problem in the future either. | Random<80 | ScoreSecurity(-3) Event(156) | ScoreSecurity(-2) | Security is reduced.
155 | 3 | Spend £3,000 on installing a "Firewall" protection system, and also spend 2 days ensuring that the new system is SET compliant (secure credit card payments over the Internet via encryption). |  | ProjectCost(3) ProjectDelay(2) ScoreSecurity(4) |  | Security increases significantly. The "Firewall" will prevent hackers accessing your internal systems, and SET compliancy will ensure that credit card payments are not intercepted.
156 | 1 | Spend a day restoring the system to it's original state. |  | ProjectDelay(1) ScoreSecurity(-1) |  | Security decreases again, obviously you still haven't learned your lesson!
156 | 2 | Spend a day restoring the system to it's original state and spend £3,000 installing a "Firewall" security system. |  | ProjectDelay(1) ProjectCost(3) ScoreSecurity(1) |  | Security increases, I hope you've learned your lesson!
159 | 1 | Explain to the group that the aim of introducing the new system is not to reduce staff (automate) but to improve the speed of the service offered to your retail outlets (transformate). |  | ScoreAcceptance(2) |  | Good approach, user acceptance increases.
159 | 2 | Take the troublemakers aside and offer them a sweetener of £2,000. |  | ProjectCost(2) ScoreAcceptance(1) |  | A slight increase in user acceptance, but it cost you £2,000 you didn't need to spend!
159 | 3 | Do nothing, how much damage can they do anyway? |  | ScoreAcceptance(-2) |  | User acceptance is reduced.
161 | 1 | Continue |  | ScoreAcceptance(1) |  | User acceptance increases.
162 | 1 | Hire an external contractor, who is an expert in JAVA, at a cost of £1,000. |  | ProjectCost(1) ScoreMorale(-1) |  | Better to invest the money in training current staff, than to pay an external contractor to do the task. Morale decreases.
162 | 2 | Remove one of your JAVA programmers from his current project duties to complete the task, delaying the project by a day. |  | ProjectDelay(1) TaskQuality(8,1) |  | Using internal staff, who better understand the system requirements, is better than hiring a contractor, who although being an expert in JAVA, won't properly understand your specific requirements.
162 | 3 | Train one of your C++ programmers in JAVA, costing £1,000. |  | ProjectCost(1) ScoreMorale(1) |  | Better to invest the money in training current staff, than to pay an external contractor to do the task. Morale increases.
164 | 1 | Hire an external consultancy to perform the analysis for you, at a cost of £5,000. |  | TaskCost(3,5) TaskQuality(3,3) Event(165) |  | An external consultant will be more objective, and be a lot more experienced in business process re-engineering. Quality increases, allowing you to concentrate on your core competencies.
164 | 2 | Perform the analysis yourself, with the help of your project team, and the users, delaying the requirements specification task by 5 days. |  | TaskDelay(3,5) TaskQuality(3,2) Event(165) |  | An external consultant would have been more objective, and be a lot more experienced in business process re-engineering. Still at least you performed the review. Quality increases.
164 | 3 | Don't carry out the review, your scarce resources would be better spent elsewhere. |  | TaskQuality(3,-2) |  | Quality decreases. Re-designing businesses processes is a key success factor for a new system.
165 | 1 | Keep the current business processes, and build the software to meet these requirements, keeping to the schedule. |  | ScoreAcceptance(-3) |  | What was the point of performing the review, if you weren't going to incorporate the changes! User acceptance decreases. Was training on the critical path?
165 | 2 | Redesign the business processes, and build the system to meet the new requirements. This will add 3 days to design and training. |  | Event(167) TaskDelay(4,3) |  | The time spent on design and training the users is increased but user acceptance is increased. Training is not on the critical path anyway, so a good move!
167 | 1 | Continue |  | TaskDelay(13,3) ScoreAcceptance(3) |  | Users not only need to understand how to operate the software but also the new business processes but they are pleased to see their changed requirements being met.
168 | 1 | Completely replace the old network, which by now is quite old technology, at a cost of £5,000. |  | ProjectCost(5) TaskQuality(7,2) Event(169) |  | A bit of a drastic approach, upgrading the network probably would have been sufficient. Quality increases.
168 | 2 | Leave the network as it is. The new system may run a little bit slower, but that shouldn't be too much of a problem. |  | TaskQuality(7,-1) Event(170) |  | Users don't like slow response times!
168 | 3 | Upgrade the network at a cost of £2,000. |  | ProjectCost(2) TaskQuality(7,1) Event(169) |  | Good decision. Quality is increased and costs are minimised.
169 | 1 | Continue |  | ScoreAcceptance(2) |  | Slow response times would have been a major cause of frustration to users. User acceptance increases.
170 | 1 | Looks like you'll have to upgrade the network after all, at a cost of £2,000. |  | ProjectCost(2) ScoreAcceptance(-1) |  | Slow response times are a major cause of frustration to users. User acceptance falls slightly.
172 | 1 | Commence a study of the supplier's system to decide how this may effect the design of the new system. This will take 2 days to complete. |  | TaskDelay(3,2) TaskQuality(3,1) Event(173) |  | Your time would be better spent performing a more thorough audit of your supply chain, to develop a more generic system.
172 | 2 | You've been thinking of replacing this supplier anyway, as they are becoming increasingly unreliable with deliveries. |  | TaskQuality(3,-1) Event(173) |  | It would still be wise to carry out an audit of your supply chain.
172 | 3 | Carry out a full audit of your supply chain, to assess the possibility of developing a generic system which could be linked to any suppliers or customers systems, taking 5 days to perform. |  | TaskDelay(3,5) TaskQuality(3,3) Event(174) |  | A good approach, quality increases.
173 | 1 | Carry out individual audits of the two supplier's systems, taking a total of 3 days. |  | TaskDelay(3,3) TaskQuality(3,1) Event(175) |  | Your time would be better spent performing a more thorough audit of your supply chain, to develop a more generic system.
173 | 2 | Tell them that you're not interested in connecting systems at the moment. |  | Event(176) |  | You could gain a lot of benefit from connecting with your suppliers systems such as the facilitation of Just-In-Time stock control.
173 | 3 | Carry out a full audit of your supply chain, to assess the possibility of developing a generic system which could be linked to any suppliers or customers systems, taking 5 days to perform. |  | TaskDelay(3,5) TaskQuality(3,3) Event(175) |  | A good approach, quality increases.
174 | 1 | Continue |  | ScoreAcceptance(2) Event(175) |  | Acceptance increases as a result.
175 | 1 | Assure them that your security is more than adequate. |  |  |  | Your security was not that good.
175 | 2 | Spend £2,000 to upgrade security. |  | ProjectCost(2) ScoreSecurity(2) |  | Good decision, security is of paramount importance when trading over external networks.
176 | 1 | You have no choice now but to carry out the audit, delaying the project by 5 days. |  | ProjectDelay(5) ScoreAcceptance(-2) |  | Acceptance also decreases.
179 | 1 | Let the testers input their own test data, slowing them down and delaying task 9 by 2 days. |  | TaskDelay(10,2) TaskQuality(5,-1) |  | Quality decreases.
179 | 2 | Convert a small subset of data from the old computer system to use for testing the software. This will delay task 9 by 3 days while the data is converted, loaded and tested. |  | TaskDelay(10,3) TaskQuality(5,1) |  | Quality increases.
180 | 1 | Perform the review, delaying the task by 2 days as a result. |  | TaskDelay(4,2) TaskQuality(4,1) Event(181) |  | Quality increases.
180 | 2 | Don't bother, the design is sound, and any problems will soon be highlighted in the programming stage. |  | Event(182) |  | It would have been sensible to carry out the audit. A day saved now could result in many day's delay later on.
181 | 1 | Continue
182 | 1 | Continue |  | TaskDelay(8,4)
183 | 1 | You come across a new supplier who has a model which exactly meets your specification. Buy from them as they are offering you a £5k discount over other suppliers and your budget. |  | TaskQuality(6,-1) TaskCost(6,-5) Event(184) |  | You don't know much about them. What kind of after sales support do they offer?
183 | 2 | Buy from your current supplier, at least you know their after-sales service is satisfactory. |  | TaskQuality(6,1) |  | Good decision. It's worth paying extra upfront if you know you can rely on the after-sales support offered. Quality increases.
184 | 1 | Delay acceptance testing for another day until the engineer arrives to fix the problem. |  | TaskDelay(17,1) |  | You should have chosen a supplier with better after-sales service.
184 | 2 | Ring the supplier again and demand they send someone immediately! |  | Event(185) TaskDelay(17,1) |  | What level of service did you buy, in the purchase contract?
185 | 1 | There's nothing you can do you'll just have to wait! |  | TaskDelay(17,1) |  | There's more to hardware than boxes!
187 | 1 | Train the users in large groups by way of a presentation of how to use the system. This will save 5 days on the training task. |  | TaskDelay(13,-5) Event(188) Event(193) |  | As the training task is not on the critical path, you would do better to spend more time training your users. User acceptance drops as a result.
187 | 2 | Train the users in small groups, at PC's, so that they can gain hands on experience of using the software. |  | Event(189) Event(194) |  | Hands-on training enhances the learning process. User acceptance increases.
187 | 3 | Provide two sets of training for each user, the 1st session being an overview presentation in large groups, and the 2nd being hands-on training at PC's in small groups, delaying training by 3 days. |  | TaskDelay(13,3) ScoreAcceptance(1) Event(189) Event(194) |  | Good decision. As the training task is not on the critical path, you can afford to spend more time training your users without delaying the project. User acceptance increases as a result.
188 | 1 | Continue |  | TaskQuality(17,-2) |  | Training is of paramount importance, and shouldn't be overlooked.
189 | 1 | Continue |  | TaskQuality(17,2) |  | The system will be much more robust as a result.
191 | 1 | Allocate some of your project team to train the support team, delaying the project by 2 days. |  | ProjectDelay(2) TaskQuality(12,1) |  | Quality increases as a result.
191 | 2 | Give the support team the system documentation and let them work it out for themselves. |  | TaskQuality(12,-1) Event(192) |  | Quality is reduced.
192 | 1 | Continue
193 | 1 | Continue |  | ScoreAcceptance(-2)
194 | 1 | Continue |  | ScoreAcceptance(1)
195 | 1 | There is little point. The system will go live soon enough anyway, and users will have a chance to try it out then. |  |  |  | Missed an opportunity to gain user support for the project.
195 | 2 | Go ahead with the plan. It will be beneficial to monitor the system being used in a live environment before it is released to all users, and will only delay the project by 2 days. |  | TaskDelay(17,2) TaskQuality(16,1) Event(196) |  | A good move to maintain quality and client commitment.
196 | 1 | Continue |  | ScoreAcceptance(2) |  | User acceptance increases.
197 | 1 | Take a phased approach, using the new system for a limited subset of the processing, while continuing with the old system for the rest. |  | Event(198) |  | This is a conservative approach which is safe but disappointed the more progressive users.
197 | 2 | Run the new and old systems in parallel for a week leading up to the live date, to be confident that the new system is operating correctly in a live environment before discarding the old system. |  | Event(199) TaskQuality(16,2) |  | Quality is increased.
197 | 3 | Shut down the old system the night before the live date, switch on the new one the next morning, to minimise duplicating work. | Random<80 | Event(222) |  | A risky approach that tests your nerve and luck!
198 | 1 | Continue |  | ScoreAcceptance(-1) |  | This was a manageable response.
199 | 1 | Continue |  | TaskCost(17,3) |  | Parallel running is safe but expensive. Is it really necessary?
200 | 1 | Force your programmers to document their own code as they produce it. This will delay the programming stage by 4 days, but will save 3 days on the documentation stage and should increase accuracy. |  | TaskDelay(8,4) TaskDelay(9,-3) Event(210) |  | Those adopting a time strategy should have considered the fact that programming is on the critical path, but documentation isn't!
200 | 2 | Hire professional consultants to produce the documentation for you, at a cost of £3,000. This should save you 3 days on documentation. |  | TaskCost(9,3) TaskDelay(9,-3) Event(211) |  | Would be better for quality to have your programmers documenting their own code. Saving 3 days on a non-critical task is a waste of £3,000!
200 | 3 | Set up a team of in-house people to document the code. This will delay the documentation activity by 3 days whilst the team are trained in documentation techniques. |  | TaskDelay(9,3) Event(210) |  | A good decision for groups following a time strategy, as Documentation is not on the critical path.
201 | 1 | Produce a summary help card of the most important functions, and provide full on screen help-text. |  | TaskQuality(9,1) ScoreAcceptance(1) |  | Quality and user acceptance both increase. Most users don't read lengthy manuals, so a summary help card is probably sufficient. Help-text is there as a good backup for more complex user functions.
201 | 2 | Produce a full user manual and full on screen help-text. Delaying documentation by 3 days. |  | TaskDelay(9,3) ScoreAcceptance(-1) TaskQuality(9,1) |  | Quality increases but user acceptance falls. Most users don't read lengthy manuals. Help-text is there as a good backup for more complex user functions.
201 | 3 | Produce a full user manual and no on screen help-text, saving 2 days on documentation. |  | TaskDelay(9,-2) ScoreAcceptance(-2) Event(203) |  | User acceptance falls. Most users don't read lengthy manuals. Users are more likely to use contex-sensitive on screen help-text.
201 | 4 | Just provide on screen help-text, saving you 3 days on the documentation activity. Nobody reads documentation anyway! |  | TaskDelay(9,-3) ScoreAcceptance(-1) TaskQuality(9,-1) Event(203) |  | Quality and user acceptance falls. Users probably will find context-sensitive help-text more useful, but some form of summary documentation would have been appropriate.
202 | 1 | Not a good idea, leave it to the professionals! |  | ScoreAcceptance(-1) |  | User acceptance falls.
202 | 2 | Good idea, the users are in a much better position to understand their own documentation requirements. |  | ScoreAcceptance(1) TaskQuality(9,-1) |  | User acceptance increases to the detriment of quality.
202 | 3 | Consult the users as to what they require, but let the professionals prepare the documentation. |  | ScoreAcceptance(1) TaskQuality(9,1) |  | User acceptance and quality are both increased.
203 | 1 | Improve the documentation, delaying acceptance testing by 2 days. |  | TaskDelay(17,2) ScoreAcceptance(1) |  | User acceptance increases. The testing would have been delayed further if the documentation hadn't been improved.
203 | 2 | Carry on with current documentation. |  | ScoreAcceptance(-1) TaskQuality(17,-1) Event(204) |  | User acceptance and quality are reduced.
204 | 1 | Continue |  | TaskDelay(17,2)
210 | 1 | Continue |  | TaskDelay(11,-2) |  | Good choice of project team!
211 | 1 | Continue |  | TaskDelay(11,2)
212 | 1 | Split the conversion into 5 phases: static data, test & rework, transaction data, test & rework, final test & rework. This approach will delay the conversion task by 5 days. |  | TaskDelay(14,5) TaskQuality(14,1) TaskQuality(15,1) |  | Quality increases at little cost since data conversion is a non-critical task.
212 | 2 | Carry on as originally planned with 3 phases: conversion, rework & testing, final rework & testing. |  |  |  | No change, but the quality increase came cheaply during a non-critical task.
212 | 3 | Save 5 days on the data conversion testing task by dropping the 'final rework & testing' phase. |  | TaskDelay(15,-5) TaskQuality(15,-2) Event(213) |  | Quality decreases with this minimalist approach to conversion and causes delay in a the critical acceptance testing task.
213 | 1 | You have no choice but to spend 3 days performing rework and testing. |  | TaskDelay(17,3) ScoreAcceptance(-1)
214 | 1 | Don't bother converting it, nobody is going to need data that old anyway. |  | TaskQuality(15,-1) |  | Quality decreases.
214 | 2 | Spend £2,000 to hire a data conversion expert to solve the problem for you. |  | TaskCost(15,2) TaskQuality(15,1) |  | Quality increases.
214 | 3 | Get one of your team to input the data manually. There isn't much data anyway, the task will only be delayed by 2 days. |  | TaskDelay(15,2) TaskQuality(15,-1) ScoreAcceptance(1) |  | Quality decreases a little, as the chances are that at least one mistake will be made when entering the data manually. Users are happy, though.
214 | 4 | Call a user group meeting to discuss the importance of the data, delaying the conversion task by 2 days. | Random<70 | TaskDelay(15,2) TaskQuality(15,1) Event(215) | TaskDelay(15,2) TaskQuality(15,1) Event(216) | The chances are the data won't be required anyway.
215 | 1 | Continue
216 | 1 | Instruct your programmers to fix the problem! |  | ScoreMorale(-1) |  | Morale decreases.
216 | 2 | Spend £2,000 to hire a data conversion expert to solve the problem for you. |  | TaskCost(15,2) TaskQuality(15,1) |  | Quality increases.
219 | 1 | Inform the user that this isn't possible to achieve, and it's not in the requirements specification anyway. |  | ScoreAcceptance(-2) |  | User acceptance falls.
219 | 2 | Get the team to look into this task. |  | Event(214) |  | A reasonable response.
220 | 1 | Send your staff on a security training course at a cost of £3,000. |  | TaskCost(13,3) ScoreSecurity(2) |  | Security increases.
220 | 2 | You're infuriated, and call a meeting to tear a strip off of your staff! |  | ScoreMorale(-1) ScoreSecurity(1) |  | Morale falls a little but the message hits home.
220 | 3 | Ignore it. They're probably just employees from another department. |  | ScoreSecurity(-2) Event(223) |  | Security falls.
221 | 1 | It was dark and his eyesight is pretty poor anyway. Just ignore him. |  | ScoreSecurity(-2) ScoreMorale(-1) |  | Security and morale both fall.
221 | 2 | Spend £3,000 on new security cameras to monitor the problem, and warn off intruders. |  | ProjectCost(3) ScoreSecurity(2) |  | Security increases.
221 | 3 | You'll investigate the problem some other time, you're a bit busy at the moment. |  | ScoreSecurity(-1) |  | Security is decreased.
222 | 1 | Continue |  | TaskDelay(18,2) ScoreAcceptance(-2) |  | A phased approach or parallel run would have been less risky.
223 | 1 | The whole project will lose 3 days whilst you re-create system data and appropriate security controls. |  | ProjectDelay(3) |  | You were lucky this was not a more serious incident.
300 | 1 | Approve the training: it will increase quality as well as the skills of your team. |  | ProjectDelay(2) BoughtResource(4) |  | A good option to support a mature development approach.
300 | 2 | Press on with the project to save time. |  |  |  | This was not a bargain unless you were really short of time.
301 | 1 | Buy the tool: that promises to increase development productivity significantly. |  | ProjectCost(10) BoughtResource(1) |  | This option saved you 2 days design / documentation time and 3 days coding.
301 | 2 | Save the money and press on. |  |  |  | OK if you were following a cost focused strategy.
302 | 1 | Buy the database for £7k to give you flexibility to meet changing data structures. |  | ProjectCost(7) BoughtResource(3) |  | Good idea in theory, and for two days saved, probably worth the price.
302 | 2 | You consider the specification to be fairly well defined. Save the money. |  |  |  | You may be surprised how unexpected requirements changes can force changes to data structures.
303 | 1 | Buy the reporting package for 5k. |  | ProjectCost(5) BoughtResource(5) |  | This saved 3 days and made users feel more involved in the project.
303 | 2 | Leave the package: your programmers are very competent at this sort of task. |  |  |  | Your programmers may be competent, but this decision lost an opportunity to draw on the skills of users and gain their buy-in to the project.
304 | 1 | Upgrade virus protection: you cannot ignore the threat. |  | ProjectCost(8) BoughtResource(6) |  | A good investment: otherwise you would be bound to have a virus attack!
304 | 2 | This looks expensive: your current package is currently up to date. |  |  |  | Foolish decision: new viruses emerge constantly and you were bound to suffer an attack!
305 | 1 | Open systems gives you hardware platform independence that might be tested in task 7. Go for it. |  | ProjectCost(8) BoughtResource(7) |  | Reasonable choice to avoid dependence on one hardware supplier. But the delay in task 7 did not seem to matter.
305 | 2 | You feel you can rely on your hardware supplier since you have been a loyal customer. |  |  |  | Commendable loyalty and although your supplier let down it did not seem to affect project time.
306 | 1 | Just think of the cost if precious development time was lost. |  | ProjectCost(6) BoughtResource(8) |  | This investment paid off, as (bad) luck would have it!
306 | 2 | You could save the money and muddle through if the worst comes to the worst. |  |  |  | The worst will come to the worst, you can be sure!