## First Sheet
TaskID | Task_Name | Mean_Task_Duration | Mean_Task_Cost
1 | Feasibility Study | 15 | 29
2 | Functional Specification | 15 | 29
3 | Requirements Analysis | 25 | 49
4 | System Design | 25 | 49
5 | Design Test Plan | 30 | 59
6 | Hardware Acquisition | 20 | 39
7 | Hardware Testing | 15 | 29
8 | Programming | 50 | 99
9 | Documentation | 20 | 39
10 | Integration Testing | 40 | 78
11 | System Testing | 20 | 39
12 | Training Plan | 20 | 39
13 | Training | 35 | 49
14 | Data Conversion | 50 | 98
15 | Data Conversion Testing | 40 | 78
16 | Acceptance Testing Plan | 50 | 98
17 | Acceptance Testing | 50 | 98
18 | Live Running | 2 | 2