## tasks
TaskID | Task_Name | Mean_Task_Duration | Mean_Task_Cost | Predecessors
1 | Feasibility Study | 18 | 87
2 | Functional Specification | 46 | 61 | 1
3 | Requirements Analysis | 16 | 39 | 2
4 | System Design | 44 | 51 | 3
5 | Design Test Plan | 34 | 9 | 2
6 | Hardware Acquisition | 16 | 90 | 4
7 | Hardware Testing | 38 | 59 | 5; 6
8 | Programming | 7 | 93 | 4
9 | Documentation | 42 | 94 | 4
10 | Integration Testing | 20 | 18 | 8; 9
11 | System Testing | 44 | 91 | 7; 10
12 | Training Plan | 19 | 24 | 4
13 | Training | 23 | 96 | 11; 12
14 | Data Conversion | 19 | 96 | 4
15 | Data Conversion Testing | 50 | 68 | 11; 14
16 | Acceptance Testing Plan | 31 | 16 | 4
17 | Acceptance Testing | 40 | 48 | 13; 15; 16
18 | Live Running | 16 | 23 | 17

## options
EventID | OptionID | Description | If | Then | Else | Comment
1 | 1 | You must find an opportunity to have a serious word with the programming team leader about this issue. | Random<30 OR TaskTime(1)>35 | Event(24) TaskQuality(10,2) ScoreMorale(2) | Event(2) | Just a warning!
2 | 1 | Review the project's morale performance. | ScoreSecurity>51 | ProjectCost(5) ProjectDelay(1) ScoreMorale(1) ScoreSecurity(2) | TaskDelay(8,1) TaskQuality(8,1) | Just a warning!

## events
EventID | Option | EventType | EventAccessLevel | AvailableFrom | Condition | Description | ImagePicture
1 | n |  | 0 |  | ScoreMorale<50 AND (Time>74 and Time<150) | Warning: morale is suffering under your iron hand; perhaps a more sympathetic approach would oil the wheels of progress!
2 | n |  | 1 |  | TaskTime(8)=32 and OnEventList(2)=1 | Warning: morale is suffering under your iron hand; perhaps a more sympathetic approach would oil the wheels of progress!

## Conditions & Actions
conditions |  |  | actions
ScoreMorale | <=> | number | ScoreMorale(number)
ScoreTime | <=> | number |  | ProjectDelay(number) | TaskDelay(number,number)
ScoreCost | <=> | number | ProjectCost(number) | Budget(number) | TaskCost(number,number)
ScoreAcceptance | <=> | number | ScoreAcceptance(number)
ScoreQuality | <=> | number |  | CurrTaskQuality(number) | TaskQuality(number,number)
ScoreSecurity | <=> | number | ScoreSecurity
Time | <=> | number
TaskTime(number) | = | number
TimeLag | = | number | TaskState(taskID)
OnEventList(number) | = | boolean | Event(number)
TaskOvertime(number) | <=> | number | BoughtRessource(number)
Random | < | number | CancelEvent(eventID)